## Roadmap
Dasu.print — Product Roadmap v0.4.0-alpha · March 2026
DONE = complete · NEXT = next sprint · PLANNED = committed · FUTURE = intention · IDEA = blue sky
Status | Theme | Feature | Description
Bug Fixes
DONE | Bug Fixes | Text element hard to select | Fixed: perPixelTargetFind disabled, text never suspended by annotate tool
DONE | Bug Fixes | Prefs panel toggle overflow | Fixed: flex layout constraint on label side, overflow-x hidden on modal body
DONE | Bug Fixes | About version auto-update | Fixed: DASU_VERSION / DASU_BUILD constants, openAbout() resolves dynamically
PLANNED | Bug Fixes | Crop lag on large SVGs | Throttle redraws during crop drag via requestAnimationFrame debounce
PLANNED | Bug Fixes | Greyscale override mixed SVGs | Colour override greyscale does not work on SVG groups containing raster images
FUTURE | Bug Fixes | DXF element panel scaling | Stroke width scaling in element panel does not reflect deeply nested DXF group objects
Smart Title Blocks
DONE | Smart Title Blocks | Assets dropdown panel | Single Assets button consolidating title block, north point, scale bar, annotation tools
DONE | Smart Title Blocks | User asset library | IndexedDB SVG asset library with thumbnail, category, insert, delete
DONE | Smart Title Blocks | Smart title block auto-fields | Tokens resolve from sheet meta — date, sheet name, status, revision, scale, drawn by etc
DONE | Smart Title Blocks | Sheet Properties panel | Right-click tab, edit all meta fields, Apply refreshes title block immediately
DONE | Smart Title Blocks | Sheet meta for drawing register | _sheets[].meta carries id, description, scale, status, revision, issueDate, drawnBy, checkedBy, purpose, discipline
NEXT | Smart Title Blocks | Read IFC data via bridge | Bridge reads IfcProject, IfcSite, IfcBuilding to populate project.name, project.address tokens
PLANNED | Smart Title Blocks | Element alias name | Allow _alias on element to override ugly filenames in title block description field
PLANNED | Smart Title Blocks | Editable title block fields | Click any TBC field on canvas to edit inline
PLANNED | Smart Title Blocks | Title block templates | Library of NZ standard title block layouts in repo assets/symbols/
PLANNED | Smart Title Blocks | Revision table in title block | Smart revision row — add revision, auto-increment letter, auto-date, description
FUTURE | Smart Title Blocks | Full token system | All title block text fields support {{token}} — resolve on render and export
FUTURE | Smart Title Blocks | IFC actor display | Show project architect, engineer, client from IFC IfcActor in title block automatically
Drawing Register
DONE | Drawing Register | Sheet Properties panel | Done via right-click tab — meta fields editable per sheet
PLANNED | Drawing Register | Drawing register modal | Sortable table — one row per sheet, all meta columns, exportable as PDF/CSV
PLANNED | Drawing Register | Export register as CSV | Batch export all sheet meta to CSV / xlsx for issue register
FUTURE | Drawing Register | Drawing issue workflow | Mark drawings DRAFT through SUPERSEDED — status reflects on title block
FUTURE | Drawing Register | Sheet set management | Organise sheets into named sets (Consent, Construction, As-built) — batch export by set
IDEA | Drawing Register | TAKT zone overlay | Overlay TAKT zone boundaries on floor plan drawings for production planning
Dimension Tool
PLANNED | Dimension Tool | Associated dimensions | Dims linked to source elements — endpoints track via position delta on move
PLANNED | Dimension Tool | Snap to vector endpoints | Dim clicks snap to path endpoints and midpoints in imported SVG geometry
FUTURE | Dimension Tool | Dim style library | Named dim styles (NZ standard, engineering, architectural) applied per drawing or globally
FUTURE | Dimension Tool | Angular dimension | Three-point angular dimension — logical extension of H/V/Aligned already done
FUTURE | Dimension Tool | Running dimensions | Chain of dims from common datum — common in NZ residential working drawings
Bonsai BIM
NEXT | Bonsai BIM | ifc: namespace metadata | Detect ifc:guid and ifc:name on SVG elements — foundation for click-to-inspect
NEXT | Bonsai BIM | Bridge SVG send confirm | Confirm end-to-end SVG send from Bonsai N-panel works with latest Bonsai 5.x
PLANNED | Bonsai BIM | Click element IFC properties | Click any element in Bonsai SVG to see IFC class, name, GUID, key properties
PLANNED | Bonsai BIM | Bonsai SVG watch folder | Bridge monitors folder for new/updated SVGs — auto-updates drawings on sheet
PLANNED | Bonsai BIM | Persistent bridge drawings folder | Bridge drawings folder persists across Blender sessions via addon preferences
FUTURE | Bonsai BIM | Multi-drawing sheet from Bonsai | Send multiple drawings to different sheets in one N-panel operation
FUTURE | Bonsai BIM | Bonsai drawing update | Re-exported drawing detected on sheet — offer to update in place
DXF
PLANNED | DXF | DXF layer manager | Per-layer visibility, colour, lineweight — NZ Drawing Standard preset
PLANNED | DXF | DXF linetype support | Dashed/dotted linetypes from DXF layer definitions rendered in SVG output
FUTURE | DXF | QCAD SVG layer detection | Detect and manage layers from QCAD SVGs (different group format to ezdxf)
FUTURE | DXF | DXF watch folder | Bridge monitors folder for new DXFs — auto-converts and places on sheet
FUTURE | DXF | DXF export | Export sheet or selected elements as DXF for consultant handoff
Assets & Symbols
DONE | Assets & Symbols | Assets dropdown | Single Assets button with sheet assets, annotation tools, user library
DONE | Assets & Symbols | User asset library | Import SVG assets, thumbnail, category, insert, delete — persists in IndexedDB
PLANNED | Assets & Symbols | NZ standard symbol library | Inkscape SVG assets: section markers, elevation markers, grid bubbles, revision clouds
PLANNED | Assets & Symbols | North point variants | Multiple north point styles selectable from Assets panel
PLANNED | Assets & Symbols | Scale bar variants | Multiple scale bar styles — auto-update when drawing scale changes
FUTURE | Assets & Symbols | Hatch pattern library | Expanded hatches: concrete, brick, earth, timber, steel, insulation, waterproofing
Annotation
DONE | Annotation | Revision cloud on shapes | Cloud linetype on any closed polygon, rect, ellipse — drawn in afterRender
PLANNED | Annotation | Rulers | H and V rulers at canvas edge showing mm at current zoom — click to place guides
PLANNED | Annotation | Guide lines | Drag from ruler to place H/V guides — snap to guides — show/hide toggle
PLANNED | Annotation | Group / Ungroup | Ctrl+G group selected elements — move and scale together — Ungroup restores
FUTURE | Annotation | Snap to custom guides | Elements snap to user-placed guides at same priority as grid and sheet edges
Canvas & UX
PLANNED | Canvas & UX | Undo / Redo | Ctrl+Z / Ctrl+Y — full command history — wired in menus, not yet implemented
FUTURE | Canvas & UX | Viewport lock per sheet | Remember zoom and pan position per sheet — restores on switch
FUTURE | Canvas & UX | Element search | Search bar in Contents panel to find elements by name or type
FUTURE | Canvas & UX | Drag reorder in Contents | Drag rows in Contents panel to reorder canvas stacking order
IDEA | Canvas & UX | Presentation mode | Full-screen sheet view, no UI, keyboard navigation between sheets
IDEA | Canvas & UX | Dark / light mode toggle | User-switchable canvas theme — currently dark only
File & Export
PLANNED | File & Export | Export all sheets PDF | Multi-page PDF with one page per sheet — currently single sheet only
PLANNED | File & Export | SVG export per sheet | Export each sheet as SVG — batch export all sheets to folder
FUTURE | File & Export | Email PDF via Outlook | Bridge triggers Outlook via win32com with PDF attached
FUTURE | File & Export | OneDrive auto-publish | On save or export, publish PDF to nominated OneDrive folder
FUTURE | File & Export | Watermark / draft stamp | Apply DRAFT or FOR CONSTRUCTION watermark across all sheets on export
IDEA | File & Export | IFC embedded drawings | Export sheet as SVG and embed back into IFC as IfcDocumentReference
Schedules & Tables
FUTURE | Schedules & Tables | Native table element | Fabric-based table — rows, cols, cell formatting for schedules on sheet
FUTURE | Schedules & Tables | CSV/IFC schedule import | Bridge converts IFC schedule or CSV to SVG table via Python — drops onto sheet
FUTURE | Schedules & Tables | Bonsai schedule support | Read Bonsai schedule of quantities/prices exports — render as table on sheet
IDEA | Schedules & Tables | Gantt chart import | Import Bonsai Gantt SVG or PNG directly onto sheet

## Gantt View
Dasu.print — Roadmap Gantt View v0.4.0-alpha · March 2026
Status column shows DONE when complete. Priority columns D–G show the status label in the active band.
Feature | Description | Status | NEXT | PLANNED | FUTURE | IDEA
Bug Fixes
Text element hard to select | Fixed: perPixelTargetFind disabled, text never suspended by annotate tool | DONE
Prefs panel toggle overflow | Fixed: flex layout constraint on label side, overflow-x hidden on modal body | DONE
About version auto-update | Fixed: DASU_VERSION / DASU_BUILD constants, openAbout() resolves dynamically | DONE
Crop lag on large SVGs | Throttle redraws during crop drag via requestAnimationFrame debounce |  |  | PLANNED
Greyscale override mixed SVGs | Colour override greyscale does not work on SVG groups containing raster images |  |  | PLANNED
DXF element panel scaling | Stroke width scaling in element panel does not reflect deeply nested DXF group objects |  |  |  | FUTURE
Smart Title Blocks
Assets dropdown panel | Single Assets button consolidating title block, north point, scale bar, annotation tools | DONE
User asset library | IndexedDB SVG asset library with thumbnail, category, insert, delete | DONE
Smart title block auto-fields | Tokens resolve from sheet meta — date, sheet name, status, revision, scale, drawn by etc | DONE
Sheet Properties panel | Right-click tab, edit all meta fields, Apply refreshes title block immediately | DONE
Sheet meta for drawing register | _sheets[].meta carries id, description, scale, status, revision, issueDate, drawnBy, checkedBy, purpose, discipline | DONE
Read IFC data via bridge | Bridge reads IfcProject, IfcSite, IfcBuilding to populate project.name, project.address tokens |  | NEXT
Element alias name | Allow _alias on element to override ugly filenames in title block description field |  |  | PLANNED
Editable title block fields | Click any TBC field on canvas to edit inline |  |  | PLANNED
Title block templates | Library of NZ standard title block layouts in repo assets/symbols/ |  |  | PLANNED
Revision table in title block | Smart revision row — add revision, auto-increment letter, auto-date, description |  |  | PLANNED
Full token system | All title block text fields support {{token}} — resolve on render and export |  |  |  | FUTURE
IFC actor display | Show project architect, engineer, client from IFC IfcActor in title block automatically |  |  |  | FUTURE
Drawing Register
Sheet Properties panel | Done via right-click tab — meta fields editable per sheet | DONE
Drawing register modal | Sortable table — one row per sheet, all meta columns, exportable as PDF/CSV |  |  | PLANNED
Export register as CSV | Batch export all sheet meta to CSV / xlsx for issue register |  |  | PLANNED
Drawing issue workflow | Mark drawings DRAFT through SUPERSEDED — status reflects on title block |  |  |  | FUTURE
Sheet set management | Organise sheets into named sets (Consent, Construction, As-built) — batch export by set |  |  |  | FUTURE
TAKT zone overlay | Overlay TAKT zone boundaries on floor plan drawings for production planning |  |  |  |  | IDEA
Dimension Tool
Associated dimensions | Dims linked to source elements — endpoints track via position delta on move |  |  | PLANNED
Snap to vector endpoints | Dim clicks snap to path endpoints and midpoints in imported SVG geometry |  |  | PLANNED
Dim style library | Named dim styles (NZ standard, engineering, architectural) applied per drawing or globally |  |  |  | FUTURE
Angular dimension | Three-point angular dimension — logical extension of H/V/Aligned already done |  |  |  | FUTURE
Running dimensions | Chain of dims from common datum — common in NZ residential working drawings |  |  |  | FUTURE
Bonsai BIM
ifc: namespace metadata | Detect ifc:guid and ifc:name on SVG elements — foundation for click-to-inspect |  | NEXT
Bridge SVG send confirm | Confirm end-to-end SVG send from Bonsai N-panel works with latest Bonsai 5.x |  | NEXT
Click element IFC properties | Click any element in Bonsai SVG to see IFC class, name, GUID, key properties |  |  | PLANNED
Bonsai SVG watch folder | Bridge monitors folder for new/updated SVGs — auto-updates drawings on sheet |  |  | PLANNED
Persistent bridge drawings folder | Bridge drawings folder persists across Blender sessions via addon preferences |  |  | PLANNED
Multi-drawing sheet from Bonsai | Send multiple drawings to different sheets in one N-panel operation |  |  |  | FUTURE
Bonsai drawing update | Re-exported drawing detected on sheet — offer to update in place |  |  |  | FUTURE
DXF
DXF layer manager | Per-layer visibility, colour, lineweight — NZ Drawing Standard preset |  |  | PLANNED
DXF linetype support | Dashed/dotted linetypes from DXF layer definitions rendered in SVG output |  |  | PLANNED
QCAD SVG layer detection | Detect and manage layers from QCAD SVGs (different group format to ezdxf) |  |  |  | FUTURE
DXF watch folder | Bridge monitors folder for new DXFs — auto-converts and places on sheet |  |  |  | FUTURE
DXF export | Export sheet or selected elements as DXF for consultant handoff |  |  |  | FUTURE
Assets & Symbols
Assets dropdown | Single Assets button with sheet assets, annotation tools, user library | DONE
User asset library | Import SVG assets, thumbnail, category, insert, delete — persists in IndexedDB | DONE
NZ standard symbol library | Inkscape SVG assets: section markers, elevation markers, grid bubbles, revision clouds |  |  | PLANNED
North point variants | Multiple north point styles selectable from Assets panel |  |  | PLANNED
Scale bar variants | Multiple scale bar styles — auto-update when drawing scale changes |  |  | PLANNED
Hatch pattern library | Expanded hatches: concrete, brick, earth, timber, steel, insulation, waterproofing |  |  |  | FUTURE
Annotation
Revision cloud on shapes | Cloud linetype on any closed polygon, rect, ellipse — drawn in afterRender | DONE
Rulers | H and V rulers at canvas edge showing mm at current zoom — click to place guides |  |  | PLANNED
Guide lines | Drag from ruler to place H/V guides — snap to guides — show/hide toggle |  |  | PLANNED
Group / Ungroup | Ctrl+G group selected elements — move and scale together — Ungroup restores |  |  | PLANNED
Snap to custom guides | Elements snap to user-placed guides at same priority as grid and sheet edges |  |  |  | FUTURE
Canvas & UX
Undo / Redo | Ctrl+Z / Ctrl+Y — full command history — wired in menus, not yet implemented |  |  | PLANNED
Viewport lock per sheet | Remember zoom and pan position per sheet — restores on switch |  |  |  | FUTURE
Element search | Search bar in Contents panel to find elements by name or type |  |  |  | FUTURE
Drag reorder in Contents | Drag rows in Contents panel to reorder canvas stacking order |  |  |  | FUTURE
Presentation mode | Full-screen sheet view, no UI, keyboard navigation between sheets |  |  |  |  | IDEA
Dark / light mode toggle | User-switchable canvas theme — currently dark only |  |  |  |  | IDEA
File & Export
Export all sheets PDF | Multi-page PDF with one page per sheet — currently single sheet only |  |  | PLANNED
SVG export per sheet | Export each sheet as SVG — batch export all sheets to folder |  |  | PLANNED
Email PDF via Outlook | Bridge triggers Outlook via win32com with PDF attached |  |  |  | FUTURE
OneDrive auto-publish | On save or export, publish PDF to nominated OneDrive folder |  |  |  | FUTURE
Watermark / draft stamp | Apply DRAFT or FOR CONSTRUCTION watermark across all sheets on export |  |  |  | FUTURE
IFC embedded drawings | Export sheet as SVG and embed back into IFC as IfcDocumentReference |  |  |  |  | IDEA
Schedules & Tables
Native table element | Fabric-based table — rows, cols, cell formatting for schedules on sheet |  |  |  | FUTURE
CSV/IFC schedule import | Bridge converts IFC schedule or CSV to SVG table via Python — drops onto sheet |  |  |  | FUTURE
Bonsai schedule support | Read Bonsai schedule of quantities/prices exports — render as table on sheet |  |  |  | FUTURE
Gantt chart import | Import Bonsai Gantt SVG or PNG directly onto sheet |  |  |  |  | IDEA
Status Legend
DONE | Complete — row is greyed, Status column shows DONE
NEXT | Committed to the next development sprint
PLANNED | Committed future work, not yet scheduled
FUTURE | Strong intention, no timeline yet
IDEA | Blue sky — worth exploring, no commitment